## Tasks
Category | Task Number | Item | Core? | How do we measure? | Proposed Metric | Deliv Assoc? | Ongoing or Project? | Project Requestor | Date Added | Contact Person | Expected Start (if Project) | Expected End | Priority | Frequency | Comments | Date Removed | Cost Saver Comments
Communications & Stakeholder Engagement | 1 | Feedback: Implement a customer satisfaction feedback and improvement process; promote customer satisfaction. | Y | C/NC |  | Y | O | BOARD |  |  |  |  | Mandate | Annually | Is this more of a metric (or method by which to measure)? Does it need to be an actual "item/activity" or can it be the means by which we measure some of the other activities?
Communications & Stakeholder Engagement | 2 | Website: host the MN HMIS website | Y | C/NC |  |  | O | BOARD |  |  |  |  | Mandate | Annually |  |  | Change method
Communications & Stakeholder Engagement | 3 | Stakeholder input: Hold quarterly stakeholder feedback meetings and/or surveys in collaboration with HMIS Governance and the CoCs to assure valuable stakeholder feedback is integrated into HMIS. | Y | C/NC |  |  | O | BOARD |  |  |  |  | Mandate | Annually
Communications & Stakeholder Engagement | 4 | Newsletter: provide email blasts to HMIS users and stakeholders for the purpose of compliance, education, awareness or input. | Y | C/NC |  |  | O | BOARD |  |  |  |  | Mandate | Annually
Communications & Stakeholder Engagement | 5 | Provide Updates: Provide updates on funder or federal policy/regulatory updates and changes related to HMIS | Y | C/NC | 1. BOARD: Provide reports on key updates neceesary/helpful to HMIS governance & management. 2. USERS: Provide updates via website & newsleters and accommodate in trainings and workflow. | Y | O | BOARD |  |  |  |  | Mandate | On demand
Communications & Stakeholder Engagement | 6 | Meeting Attendance: Staff and engage in Statewide HMIS, CoC, and Homeless meetings at the request of HMIS Governance. | Y | C/NC | 1. State: 100% represenation at monthly Board meeting. 2. ___% attendance at CoC meeting. | Y | O | BOARD |  |  |  |  | Mandate | Other (see comments) | As requested by the board. ICA currently chairs the HHA Data Committee and sits on the HHA Policy and Outcome Alignment Committee. |  | Change quantity, method
Data Quality & Integrity | 7 | Support Data Quality: Monitor data quality and train end users, agencies and the CoC to obtain and retain a high level of data from all CHOs; | Y | Both | Quarterly data quality reports, education on data quality. |  | O | BOARD |  |  |  |  | Mandate | Quarterly
Data Quality & Integrity | 8 | Policies: Implement and monitor a security plan, an updated data quality plan, and a privacy policy to the CoC on a timeline agreed on by the CoC, HMIS Governing Group and HMIS Lead and in accordance with all HUD rules, notices, and guidance establishing the requirements of these plans. The HMIS Lead, in conjunction with the HMIS Governing Group and CoC, must review and update the plans and policy at least annually. During this process, the HMIS Lead must seek and incorporate feedback from the CoCs, State Agencies and other HMIS stakeholders. | Y | C/NC | By January Board meeting present updates to HMIS security, data quality and privacy policy. | Y | O | CoC all |  |  |  |  | Mandate | Annually
Data Quality & Integrity | 9 | Continual Performance: Assure system performance, including the ongoing availability and accessibility of the HMIS software and system. | Y | Both | 99% availability with a maximum of 3 second response time as reported by ICA and end users. Does not include loss of system access or functionality controlled by Bowman. |  | O | BOARD |  |  |  |  | Mandate | Ongoing
Data Quality & Integrity | 10 | Data Privacy/Security Compliance: Operate HMIS in compliance with data privacy and data security regulations/requirements (state, federal, and funder), assuring providers are trained and monitored on how to support compliance. | Y | Both |  | ? | O | BOARD |  |  |  |  | Mandate | Ongoing
Data Quality & Integrity | 11 | Data quality reports: Provide a minimum of quarterly reports to CoCs on data quality. Make recommendations for improvement to data quality and support local agencies, state agencies and CoCs on continuous quality improvement efforts. | Y | C/NC |  |  | O | CoC all |  |  |  |  | Mandate | Quarterly
Data Quality & Integrity | 12 | Uploads: Support data uploads to ServicePoint | y | C/NC | List of successful vs. unsuccessful data uploads. | Y | O |  | 2016-08-04 |  |  |  | Medium | On demand |  |  | Cuttable
Management & Compliance | 13 | Bowman Contract: Manage and negotiate Bowman vendor contract on behalf of HMIS Governance and provide updates on Bowman and ServicePoint to stakeholders | Y | C/NC | Successful execution of annual contract approved by Board. |  | O | BOARD |  |  |  |  | Mandate | Annually
Management & Compliance | 14 | NOFA: Contribute to narrative portions of the Continuum of Care Program Competition Collaborative Application as appropriate | Y | C/NC | Contribution of accurate documents by agreed upon deadline. |  | O | CoC all |  |  |  |  | Mandate | Annually
Management & Compliance | 15 | Agency participation: Facilitate, monitor, and report to CoC the participation of all agencies submitting data to HMIS and ensuring compliance with federal HMIS requirements; Adhere to MN HMIS Policies and Procedures. Make recommendations to HMIS Governance on improvements to policies related to compliance, system quality or functionality | Y | Both | Provide report on: # of agencies by CoC, if this is increase/decrease; and concerns with compliance or utilization. Integrate recommendations for improving quality participation. | Y | O | CoC all |  |  |  |  | Mandate | Ongoing
Management & Compliance | 16 | Support Policies: Implement and maintain compliance with written HMIS policies and procedures as approved by the statewide governance committee and in accordance with § 580.31 for all CHOs; | Y | Both |  |  | O | BOARD |  |  |  |  | Mandate | Ongoing
Management & Compliance | 17 | Participation Agreement: Execute a written HMIS Participation Agreement with each participating CHO, ensuring the agreement includes: the obligations and authority of the HMIS Lead and CHO, the requirements of the security plan and privacy policy with which the CHO must abide, sanctions for violating the HMIS Participation Agreement, and an agreement that the HMIS Lead and the CHO will process Protected Identifying Information consistent with the agreement; | Y | C/NC | Update & tracking of Participation Agreement by 3/1/17 | Y | O | CoC all |  |  |  |  | Mandate | On demand
Management & Compliance | 18 | Work Plan: Participate in the design of and follow the HMIS Governance Annual Work Plan, which includes; reporting standards, budget, priorities, policies, and directives. | Y | Both | Provide monthly updates to the board . | Y | O | BOARD |  |  |  |  | Mandate | Other (see comments) | Annual work plan, monthly reports
Management & Compliance | 19 | State Reports: Assure State program reports are accurate and available by agreed upon deadline (ESG, ESP, Healthy Transitions, HYA, LTH SS, PATH, THP, FHPAP, LTH & Unduplicated Programs Report). | Y | C/NC | Work with State Agencies to assure completion by agreed about timeline. |  | O | HUD |  |  |  |  | Mandate | Annually
Management & Compliance | 20 | HUD Project Applicant/SSA: Serve as the applicant to the US Department of Housing and Urban Development (HUD) for CoC grant funds to be used for HMIS activities for the CoC’s geographic area, as directed by the CoC in consultation with the statewide Governance committee, and entering into grant agreements with HUD to carry out the HUD-approved HMIS activities; | Y | C/NC | Timely submission of application and pre-application materials to each CoC. |  | O | CoC all |  |  |  |  | Mandate | Annually
Management & Compliance | 21 | HMIS Standards: Operate HMIS in compliance with current HMIS Technical Standards, HUD HMIS Data Standards and other applicable state or federal laws, assuring providers are trained and monitored on how to be compliant with said standards and laws. | Y | Both |  |  | O | CoC all |  |  |  |  | Mandate | Not applicable
Management & Compliance | 22 | Financial Management: Report financial and resource expenditures to assure transparency in resource management, prioritization, and operations. Provide budget reports that clearly compare fiscal year-to-date actuals (income and expenses), summarized by categories, to original and revised budgets. | Y | C/NC | Provide annual and quarterly budget reports to Governance and on demand to finance committee. | Y | O | BOARD |  |  |  |  | Mandate | Other (see comments) | quarterly reports and on demand by finance committee
Management & Compliance | 23 | Customized reports: Respond to and support requests from Continuums, state partners, and agencies for customized reports. | Y | C/NC | Respond to requests within 2 business days. Follow HMIS Governance protocol on prioritization when there is a bottleneck. | Y | O | [5 empty] | Mandate | Annually |  |  | Change quantity
Management & Compliance | 24 | Coverage: Review, monitor and report HMIS coverage rates to the CoC and HMIS Governance, making recommendations and supporting improved coverage. | Y | C/NC | Monthly coverage reports including changes. | Y | O | BOARD |  |  |  |  | Mandate | Annually | This has to be a collaborative process - must have information from CoCs on the total number of beds in their area to be able to calculate the % of beds covered.
Management & Compliance | 25 | HUD Reports: Assure HMIS information/reports are accurate and available for required HUD mandates/reports including, but not limited to: SYP's, NOFA, PIT, HIC, APR, AHAR) and data required for annual NOFA competition. | Y | C/NC | Work with CoCs to assure completion in a timely manner. |  | O | HUD |  |  |  |  | Mandate | Annually
Management & Compliance | 26 | PIT Counts: Work with CoCs, DHS and State Office to Prevent and End Homelessness to plan for, execute and report on statewide point-in-time counts. | Y | C/NC |  | Y | P | CoC all | 2016-08-02 | Amy Stetzel |  |  | High | Annually |  |  | Change method, quality
Management & Compliance | 27 | Status Updates: Report the status of deliverables identifying any relevant information related to responsibilities (issues, delays, challenges, solutions, recommendations, etc.) | Y | C/NC | Monthly updates to Board. | Y | O | BOARD |  |  |  |  | High | Monthly
Management & Compliance | 28 | System Operations: Conduct day-to-day operational requirements of the HMIS software and system; | Y |  |  |  | O | [5 empty] | Mandate | Annually
OUTCOME | 29 | Maximize use of HMIS: Support the broad use of HMIS as a tool to document, serve and end homelessness. Encourage and support using HMIS to its maximum potential, including increasing functionality, incorporating innovations, and assuring adaptivity. | Y |  | 1. Identify system functions or innovations that will improve efficiencies, workflow, data quality, performance, or outcomes. 2. Support and train on the utilization of enhanced and customized system functions that enable agencies and CoCs to improve quality of service, gain efficiencies, reduce duplication of data entry and encourage overall desire to utilize HMIS as a tool to prevent and end homelessness. | Y | O | CoC all |  |  |  |  | Mandate | On demand |  |  | Change quality
Staffing | 30 | Metro: Provide a minimum of 4 metro/suburban-metro system administrator (SA) positions. |  | C/NC
Staffing | 31 | Greater Minnesota: Provide a minimum of 3 greater Minnesota SAs with regional office locations |  | C/NC
Staffing | 32 | Help Desk: Provide SA and analyst staffing of help desk services. Hours: 8-4 or 9-5 workdays AND provide after-hours emergency response to system outages. Requests for help should be responded to within 4 hours. |  | C/NC
Staffing | 33 | Data Analyst: Provide a minimum of 1 full-time data analyst for Minnesota’s HMIS. |  | C/NC
Staffing | 34 | Report Writer: Provide a minimum of 1 report writer. |  | C/NC
Staffing | 35 | Project Manager: Provide 1 project manager. |  | C/NC
Systems Modifications | 36 | Coordinated Entry: Assist the Continuums of Care with design and implementation of their Coordinated Entry System within HMIS; | Y | C/NC | By 11/1/16: 1. Develop customized assessments for each CoC (at least 1 Access, Assessment and Prevention for each CoC); 2. set-up prioritization lists for each CoC; 3. set-up and Workflow; 4. CoC & State reports; 5. assure sharing; and 5. Provide training. |  | P | CoC all |  |  | 2016-06-01 | 2016-12-31 | High | Not applicable
Systems Modifications | 37 | Customized Assessments: Support State agencies, CoCs and agencies in developing customized assessments. | Y | C/NC |  | Y | P | Community - all |  |  |  |  | Mandate | Annually |  |  | Change quantity
Systems Modifications | 38 | Modules: Support the immediate addition, set-up, training, and customization for HMIS Modules into system functions including Call Point and Fund Manager. | Y | C/NC | By 11/1/16: | Y | P | CoC all |  |  |  |  | Mandate | Annually |  |  | Cuttable
Systems Modifications | 39 | Modules: Support the addition, set-up, training, and customization for HMIS Modules into system functions for Eligibility Point. | Y | C/NC | By ???? | Y | P | CoC all |  |  |  |  | Mandate | Annually |  |  | Change quantity
Systems Modifications | 40 | LSA - Working with CoCs, Complex Agencies and HMIS Governance to determine role of Local System Administrators. | Y | C/NC | By 3/1/17 |  | P | Community - all
Training | 41 | New User Trainings: Provide new user and refesher trainings online. | Y | C/NC | update trainings by 10/15/16 | Y | O | [5 empty] | Mandate | Annually
Training | 42 | Program specific training: Provide customized trainings for specific programs to help assure all data elements and other funder requirements are understood and reported. | Y | C/NC | update trainings by 10/15/16 | Y | O | BOARD |  |  |  |  | Mandate | Annually
Training | 43 | Administrator Trainings: Provide trainings for administrators (agencies, Coordinators, funders, and planners) on how to use HMIS to: enhance performance (program and system), support planning, and assure compliance. | Y | C/NC |  | Y | O | Community - all |  |  |  |  | Mandate | Annually
Special Projects | 44 | Adult Shelter Connect: Ongoing training and support. | [5 empty] | CoC Hennepin
Special Projects | 45 | Upgrade ServicePoint to 6.0 (MUST be completed no later than 10/1/18) | [9 empty] | 2018-10-01
Special Projects | 46 | Replace reporting software with QLIK
Special Projects | 47 | GRH-LTH Project | [5 empty] | DHS
Special Projects | 48 | Rewrite training curriculum for SP 6.0
Special Projects | 49 | Develop and implement workflows in 6.0
Special Projects | 50 | Rewrite training curricuum for QLIK
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
Note on E1: Amy L Highness: Complete/Not Complete Metric Both

## List values
Priority | Frequency | Requestor
Mandate | Not applicable | Catholic Charities
High | On demand | CoC all
Medium | Annually | CoC Central
Low | Quarterly | CoC Hennepin
| Monthly | CoC NE
| Weekly | CoC NE
| Ongoing | CoC NW
| Other (see comments) | CoC Ramsey
CoC River Valleys
CoC SMACC
CoC St Louis
CoC West Central
Community - all
DHS
HUD
MAC-V
MHFA
Salvation Army
Simpson Housing
Union Gospel Mission
Veterans
BOARD

## history log
Date | By | Comment
2016-07-27 | Jennifer Trombley | Added Diane Elias Prevention Study task #63
2016-08-02 | Jennifer Trombley | Added PIT Count as core work
2016-08-04 | Jennifer Trombley | Support data uploads to ServicePoint
2016-08-30 | Jennifer Trombley | updated many columns